## Introduction
Community Readiness and Resilience Planning Toolkit Workbook
Resilient Communities have the ability to proactively prepare for and adapt to changing conditions. They are flexible, resourceful, learn from past experiences, and plan for future events. They can withstand chronic stressors and bounce-forward from sudden shocks. Resilient Communities rebound, positively adapt to, and thrive amidst changing conditions or challenges — including human-caused and natural disasters — and maintain quality of life, healthy growth, durable systems, economic vitality, and conservation of resources for present and future generations. However, this is a constant and incredible challenge for communities. As such, the Colorado Resiliency Office has created this workbook to support communities with this challenge. The following workbook is meant to be used in conjunction with the Community Readiness and Resilience Planning Toolkit (https://www.coresiliency.com/resilience-step-1) provided by the Colorado Resiliency Office, that can be used by your community to complete community readiness and resilience planning.
Included in this workbook:
Step 1 Activity 1 | Community Plans
Step 1 Activity 1 | Work Plan Timeline
Step 1 Activity 1 | Project Schedule
Step 1 Activity 1 | Budget Sheet
Step 1 Activity 2 | Planning Team Worksheet
Step 1 Activity 3 | Stakeholder Mapping
Step 1 Activity 4 | Community Engagement Plan
Step 2 Activity 1 | Resources and Guides
Step 2 Activity 1 | Shocks and Stressors
Step 3 Activity 1 | Assess Vulnerability
Step 3 Activity 1 | Assess Risk
Step 3 Activity 1 | Risk Matrix
Step 4 Activity 2 | Resilience Strategies
Step 4 Activity 2 | Evaluation
Step 4 Activity 2 | Final Actions
Step 5 Activity 3 | Implementation Team
Step 5 Activity 4 | Action Implementation

## S1A1 Community Plans
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 1
Community Plans
Creating a resilient community does not mean that you need to start from scratch. It can be useful to start by inventorying your community’s existing plans and policies and determining which of those already include information on, and strategies to address current and future projected shocks and stressors to your community. This spreadsheet can help you keep track of your communities inventories. Also a list of useful plans can be found on the Colorado Resiliency Office Website (https://www.coresiliency.com/resiliency-resources).
Relevant Community Plans
Title | Author(s) | Date | Link | Notes/ Summary | What resilience or recovery areas are covered by the plan? | Additional Notes

## S1A1 Workplan Timeline
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 1 Workplan Timeline
Generally speaking, the development of a specific plan (e.g., a pre-disaster recovery plan or a climate change adaptation plan) can take anywhere between 6-24 months. Yet the timeline for developing a general community resilience framework may take between 3-6 months. Plan updates (e.g., a Comprehensive Plan) can generally take 6-14 months depending on the community, plan, and allotted time frame. The timeline of your project may also be determined based on specific grant requirements. Use the template workplan to fill in the description and time frame columns with details specific to your planning process, taking into account the considerations listed below. You can also use the Gantt chart provided in the next tab.
PLANNING PROCESS WORKPLAN AND TIMELINE
| Phase | Step | Description | Time Frame
| Phase 1 | 1.1 Motivation and Scope
1.2 Team and Resources
1.3 Climate Effects and Community Elements
1.4 Outreach and Engagement
| Phase 2 | 2.1 Exposure
2.2 Sensitivity and Potential Impacts
2.3 Adaptive Capacity
2.4 Vulnerability Scoring
2.5 Outreach and Engagement
| Phase 3 | 3.1 Summarize Vulnerability
3.2 Confirm Vision and Goals
3.3 Prepare Adaptation Strategies
3.4 Prioritize Adaptation Strategies
3.5 Outreach and Engagement
| Phase 4 | 4.1 Implement
4.2 Monitor
4.3 Evaluate
4.4 Adjust
WHAT IS THE TIME FRAME FOR THE PLANNING PROCESS?
Like all other planning efforts, resiliency planning requires time and effort. Local government agency staff and other stakeholders will need to commit their time, technical and financial resources, and the available knowledge of everyone involved to ensure a successful process.
The time frame for the adaptation planning process may be determined by a grant, budget cycle, direction from elected officials, community priorities, or other factors. The breakdown of a sample adaptation planning process shows the phases and steps in this process. Steps may take more or less time depending on capacity, funding, scope details, and other characteristics. Following all phases could take 12 to 24 months, depending on the level of detail and resources committed to each phase. It is also possible to work on more than one step at the same time. This type of table can be updated to account for any resiliency planning process.
Considerations that can affect the time frame of the process are:
Staff Capacity: Availability of local agency staff and other stakeholders who will lead and/or participate in the planning process.
External Support: Need for external support from consultants, community partners, or other external partners to complete the process.
Data: Data availability from internal and external providers and whether any new technical studies are needed.
Community Engagement: Commitment to community and stakeholder engagement (beyond those who are leading the process), including types and timing of events and opportunities.
External Review: Requirements for review and participation by external agencies. Some planning mechanisms, such as general plan safety elements or local hazard mitigation plans, require review by external agencies that can take many months.

## S1A1 ProjectSchedule
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 1 Project Schedule
Generally speaking, the development of a specific plan (e.g., a pre-disaster recovery plan or a climate change adaptation plan) can take anywhere between 6-24 months. Yet the timeline for developing a general community resilience framework may take between 3-6 months. Plan updates (e.g., a Comprehensive Plan) can generally take 6-14 months depending on the community, plan, and allotted time frame. The timeline of your project may also be determined based on specific grant requirements. You can also use the Gantt chart to track your progress or plot your project timeline. Note the prior tab in this workbook can also be utilized.
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Project Title:
Enter Company Name in cell B2. | Company Name:
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead:
| Project Start: | 2021-06-17
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Display Week: | 1 |  |  |  |  | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | time axis 2021-06-14 to 2021-08-08
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-06-14 to 2021-08-08
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4.
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Phase 1 Title
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 1 | Name | 50% | 2021-06-17 | 2021-06-20 | 4
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 2 |  | 60% | 2021-06-20 | 2021-06-22 | 3
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 3 |  | 50% | 2021-06-22 | 2021-06-26 | 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 4 |  | 25% | 2021-06-26 | 2021-07-01 | 6
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 5 |  |  | 2021-06-21 | 2021-06-23 | 3
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Phase 2 Title
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 1 |  | 50% | 2021-06-22 | 2021-06-26 | 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 2 |  | 50% | 2021-06-24 | 2021-06-29 | 6
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 3 |  |  | 2021-06-29 | 2021-07-02 | 4
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 4 |  |  | 2021-06-29 | 2021-07-01 | 3
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 5 |  |  | 2021-06-29 | 2021-07-02 | 4
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Phase 3 Title
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 1 |  |  | 2021-07-02 | 2021-07-07 | 6
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 2 |  |  | 2021-07-08 | 2021-07-12 | 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 3 |  |  | 2021-07-13 | 2021-07-18 | 6
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 4 |  |  | 2021-07-19 | 2021-07-23 | 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 5 |  |  | 2021-07-13 | 2021-07-17 | 5
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Phase 4 Title
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 1 |  |  | date | date | #VALUE!
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 2 |  |  | date | date | #VALUE!
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 3 |  |  | date | date | #VALUE!
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 4 |  |  | date | date | #VALUE!
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | Task 5 |  |  | date | date | #VALUE!
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download.

## S1A1 Budget Sheet
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 1 Budget Sheet
Funding to support your resilience planning work may determine your project scope, timeline, community engagement efforts, and more. As in any planning effort, there are likely budget items that are critical to the success of your project, and items that are optional, but may add value. This spreadsheet may be utilized to help you create your project budget. There are also many places to obtain funding to support your resilience planning work in your community. If you are doing resilience planning prior to having secured funding, you will need to identify potential funding opportunities to support your work. Funding sources include municipal, county, federal or state grants, private foundations, university research partnerships, non-profit initiatives, business partnerships, etc. The Colorado Resiliency Office has a list of funding sources that can be accessed here (https://www.coresiliency.com/funding-resources).
Budget Template
| COST CATEGORY | Title/ | Rate | # of units | Salary | Benefits | Total
|  | Description | (per unit) | (hours, meetings, etc.) | (D*E) |  | (F+G)
PERSONNEL
Totals
PARTNERS, SUB APPLICANTS AND CONSULTANTS
Totals
SUPPLIES
Equipment
Meeting supplies
Materials
Production/print costs
Meeting refreshments
Totals
OTHER DIRECT COSTS
Facility Rental
Training
Financial support for community stakeholders and participants
Transportation
Totals
INDIRECT COSTS
Totals
COMBINED TOTAL
Project Costs

## S1A2 Planning Team Worksheet
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 2 Planning Team Worksheet
Brainstorm a list of potential individuals within your department, staff, or broader community, to fill the roles of community engagement lead, project coordinator, subject matter experts, and research and writing staff. Ideally, your team will consist of a great project manager, community engagement expert, project coordinator, and research and writing staff. Communities with limitations in capacity and/or staffing should look to outside organizations in the community to support the process including: scientific researchers, business community leaders, non-profit partners, or state and federal agencies. The size of your team may vary, but generally consists of 3-8 team members and should appropriately represent your community and ensure that all members are actively participating. Depending on the scope of your project, core team members should be willing to commit to participating throughout the course of the project (6-24 months depending on the project) to see the process through. Consider the individuals on your list and determine whether or not they are a good fit based on several criteria. Once you select individuals, invite them to participate and confirm their commitment to that role. Consider advisory committee members across all six of the sectors identified in the 2020 update to the Colorado Resiliency Framework: 1) Community; 2) Economic; 3) Health and Social; 4) Housing; 5) Infrastructure; and 6) Watersheds and Natural Resources.
Planning Team
Last Name | First Name | Organization | Sector | Position/Department | Notes | Email | Phone
300 Tamalpais Drive, Corte Madera, CA

## S1A3 Stakeholder Mapping
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 3 Stakeholder Mapping
This workbook will help you map the stakeholders relevant to your project. You may not be able to identify individuals for all potential stakeholder roles, but this list will help you get started. Please add additional stakeholder groups that may be relevant to your community. This includes your core team, your advisory committee, and potential stakeholders you would like to engage with throughout the process. Identify each group's general interest, influence, expertise, as well as potential challenge areas in effectively communicating or engaging with them. Consider the ways in which historically and currently underrepresented leaders in your community have or have not been involved in planning processes and ensure that you have identified a clear, equitable, and effective process for involving those leaders in this process. Consider community members across all six of the sectors identified in the 2020 update to the Colorado Resiliency Framework: 1) Community; 2) Economic; 3) Health and Social; 4) Housing; 5) Infrastructure; and 6) Watersheds and Natural Resources.
STAKEHOLDER MAPPING
| Agency/Entity | Contact | Reason for Including Stakeholder | High Influence, Low Interest | High Influence, High Interest
Project Team
Comprehensive planning
Land use
Transportation
Public works
Local emergency planning/management
Geographic information systems
Advisory Group
Local Agencies
Building code enforcement
| Fire departments/districts |  |  | Low Influence, Low Interest | Low Influence, High Interest
Floodplain administration
Parks and recreation
Public information office
Natural and cultural resources
Stormwater management
Transportation (roads/bridges)
Finance
Economic development
Housing
Health and social services
Solid waste management
Special Districts and Authorities
Utility districts
Parks districts
Public and private schools
Public and private hospitals
Non-governmental Organizations
Community-based organizations
Private sector businesses, economic development entities, or business groups
Faith-based organizations
County, State, and Federal Partners
State office of emergency services
State energy office
State office of housing and community development
State planning office
State water agencies
FEMA
Leadership and Decision Makers
City Council/Board of Commissioners
City/County Planning Commission
Other officials
Interest Groups
Environmental groups
Social justice groups
Neighborhood groups
CERT teams
Cultural groups

## S1A4 Community Engagement Plan
Community Readiness and Resilience Planning Toolkit Workbook: Step 1 Activity 4 Community Engagement Plan
This workbook will help you figure out the best way(s) to reach your stakeholders. Some key questions to consider include: * How many public workshops are needed and appropriate? * How much time do you have to facilitate the community engagement process? * Which aspects of your community engagement plan are critical, and which are optional? * How can you ensure that the project is supporting historically and currently underrepresented community members and their involvement/communication needs?
Target Audience: Utilize the work you completed in the prior tab to identify target audiences. Make sure each the project includes targeted outreach to each group.
Channel/Engagement Tools: The following is a list of examples: * Creating a plan website that is updated regularly with plan information and meeting details; * Using online or in-person surveys to understand community needs; * Developing outreach materials like posters, brochures, and memos for distribution; * Conducting individual interviews or focus groups to better understand community needs and help create strategies; using social media channels to distribute information about the plan and public meeting details; * Printed materials and posters in community kiosks distributed at key locations in the town or city; * Community workshops; * Plan newsletters; * Creating unique and innovative ways to showcase information including ArcGIS Story Maps; * Engaging youth, older adults, and frontline community members by speaking at and soliciting support from schools, community groups, and nursing homes among others; * Seeking out and making connections with journalists and/or radio hosts from local and regional media organizations to better publicize the planning effort and process; and, * Creating formal and informal tools to solicit feedback at key stages of the process. Additional resources on effective community engagement can be found in Community Readiness and Resilience Toolkit.
Engagement Type: This is defined by the visual on the right.
Key Messaging: Key messages are the primary points of information you want your audience to hear and understand.
Estimated Costs: How much you think this type of outreach will cost.
Number of Touch Points and Timeline: How often and when you will use these outreach methods.
Target Audiences | Channel/Engagement Tools | Engagement Type (Inform, Consult, Involve, Collaborate, Empower) | Key Messaging | Estimated Costs | Number of Touch Points and Timeline

## S2A1 Resources and Guides
Community Readiness and Resilience Planning Toolkit Workbook: Step 2 Activity 1 Resources and Guides
There are a variety of important data sources available to you at the State and Federal level. A list of useful plans can be found on the Colorado Resiliency Office Website (https://www.coresiliency.com/resiliency-resources).
Resources and Guides
Title | Author(s) | Date | Link | Notes/ Summary | Additional Notes

## S2A1 Shocks and Stressors
Community Readiness and Resilience Planning Toolkit Workbook: Step 2 Activity 1 Identify Shocks and Stressors
This worksheet will help you identify shocks and stressors that have, are, and will continue to impact your community. As defined in Step 1, shocks and stressors may be specific to your community or region. Defining those shocks and stressors are key to understanding how they may be changing and how you can develop resilience strategies to address them. It may also be useful to outline shocks and stressors as they apply to critical sectors, especially in places where agriculture, recreation, or other climate- and weather-sensitive livelihoods play a major role in overall community well-being, as these sectors are known to have unique and often complicated reactions to both hazards and background stressors. Workshops focused on this topic with sector experts and community members is one way to accomplish this goal. Similarly, soliciting input on this topic from experts in healthcare, non-profit, faith, and community service sector experts can give critical insights into how the most vulnerable members of your community might face unique challenges as disaster processes unfold. The Colorado Resilience Office has many resources to help with this task {https://www.coresiliency.com/resiliency-resources}.
IDENTIFY SHOCKS AND STRESSORS
| Shock/Stressor | Who is Impacted in the Community | What Sector(s) is Impacted? | Has this Happened Before? | If so, When? | How can the community improve the Response/Recovery?

## S3A1 Assess Vulnerability
Community Readiness and Resilience Planning Toolkit Workbook: Step 3 Activity 1 Assess Vulnerability
This tab will help your team assess potential vulnerabilities of key assets in your community. A few examples are provided in red below.
This template is based off of the U.S. Climate Resilience Toolkit (https://toolkit.climate.gov/steps-to-resilience/assess-vulnerability-risk).
Definitions
Key Asset or Resource – People, resources, ecosystems, infrastructure, and the services they provide. Assets are the tangible and intangible things people or communities value. Weather or Climate Hazard (Exposure) - An extreme weather event or changing climate condition that can adversely affect people, livelihoods, species, ecosystems, environmental functions, services, resources, infrastructure and economic, social, and cultural assets. Time Frame - The projected time frames for climate trends. If specific dates are associated with a projected trend, those can also be listed (e.g., such as Medium-term or 2030-60); Short-term (within 15 years or already occurring); or, Long-term (occurring between 2050-2100). Potential or Historical Consequences – Potential consequences of exposure to a climate hazard based on historic conditions. Sensitivity - The degree to which community function, structures, and populations are affected by a climate exposure. These are ranked as Low, Medium, or High. Provide a short description of the justification for the ranking. Adaptive Capacity - The potential of a person, asset, or system to adjust to a hazard to limit damage, take advantage of opportunities, and cope with change. Rank as Low, Medium, or High. Vulnerability - The degree to which something is susceptible to or predisposed to adverse effects of hazards as determined by exposure, sensitivity, and adaptive capacity. Rank as Low, Medium, or High. Other Stressors - Past and ongoing stressors that exacerbate risk (e.g., air pollution from vehicles which exacerbates asthma or other respiratory diseases, or development in the Wildland Urban Interface which exacerbates risk to wildfire to homes and businesses).
Key Asset or Resource | Projected Weather or Climate Hazard (Exposure) | Projected Time Frame | Potential Consequences of Hazard | Sensitivity of the Asset (Rank Low, Medium, or High) | Adaptive Capacity of the Asset (Rank Low, Medium, or High) | Total Vulnerability (Rank Low, Medium, or High) | Other Stressors to Consider
Hospital | Flooding | Mid-term | Electrical outage due to no back up generator, in ability to access or egress the hospital due to flooded transportation routes. | High | Low | High | New construction upstream increasing the area of impermeable surface
Community Center Building | Extreme precipitation events | Mid-term | Closed for repair, temporary loss of meeting location | Low | High | Low | Large parking lot uphill from the buildings main door
Elderly Residents | Extreme heat days (days above 100 degrees Fahrenheit) projected to double by the 2050s | Near-term (already happening) | Heat-related illnesses, even death | Medium | Medium | Medium | Lack of air conditioning and limited mobility

## S3A1 Assess Risk
Community Readiness and Resilience Planning Toolkit Workbook: Step 3 Activity 1 Assess Risk
This tab will help your team assess your community's risks to the vulnerabilities previously identified. In column A below, list the most vulnerable or important-to-protect assets identified in the Assess Vulnerability Tab. For each asset, rank the probability of a Loss as high, medium, or low. Next rank the magnitude of the potential loss. Once your table is complete, use the rankings to place each asset in the appropriate section of the Risk Characterization Matrix in the next tab (Risk Matrix).
This template is based off of the U.S. Climate Resilience Toolkit (https://toolkit.climate.gov/steps-to-resilience/assess-vulnerability-risk).
Most Vulnerable Assets | Probability of a Loss (Rank Low, Medium, or High) | Magnitude of a Loss (Rank Low, Medium, or High)

## S3A1 Risk Matrix
Community Readiness and Resilience Planning Toolkit Workbook: Step 3 Activity 1 Risk Matrix
This tab will help your team define your risk based on the magnitude of a potential loss and the probability of a potential loss.
This template is based off of the U.S. Climate Resilience Toolkit (https://toolkit.climate.gov/steps-to-resilience/assess-vulnerability-risk).
Plot the vulnerabilities from the previous tab into the risk matrix to determine the relative risk of each asset or area of concern.
|  |  | Magnitude of a (Potential) Loss |  | Relative Risk
|  | Low | Medium | High | Low
| High |  |  |  | Medium
Probability of a (Potential) Loss | Medium |  |  |  | High
| Low |  |  |  | Very High

## S4A2 Resilience Strategies
Community Readiness and Resilience Planning Toolkit Workbook: Step 4 Activity 2 Resilience Strategies/Actions
This tab will help your team organize the resilience strategy/action ideas from a variety of sources, including those that your community is already using. See the Community Readiness and Resilience Toolkit for more details on this activity.
Resilience strategies and actions (ideas from local, regional, state, and national plans as well as stakeholders, case studies, reports, etc.) | Source and Relevant links | Comments | Resilience Value
Strategy 1:
Action 1
Action 2
Action 3
Strategy 2:
Action 1
Action 2
Action 3
Strategy 3:
Action 1
Action 2
Action 3
Strategy 4:
Action 1
Action 2
Action 3
Strategy 5:
Action 1
Action 2
Action 3

## S4A2 Evaluation
Community Readiness and Resilience Planning Toolkit Workbook: Step 4 Activity 2 Evaluation Worksheet
This tab is intended to help your team evaluate resilience actions as organized underneath their appropriate strategies. Using the approach agreed upon by your core team, complete the evaluation process to determine which actions are the best potential fits for your community. A systematic approach to evaluation will help you determine: 1) which actions are not relevant or are not a good fit for your community; 2) help you rank/rate your actions; and, 3) set you up to refine and prioritize actions. Many communities choose to rank their actions by effectiveness, efficiency, and feasibility. By scoring every individual action, you can better systematically determine how to best invest the existing resources and better plan for the future. You may choose to eliminate actions that rank very low.
Effectiveness: The extent to which the resilience action achieves the desired outcomes. | [7 empty] | Evaluation Rating Definition:
Does the resilience action meet your resilience goals? Does it meet one (or more) of your resilience goals? | [7 empty] | 1 | Limited or No Effectiveness/Efficiency/Feasibility
Does the resilience action address key vulnerabilities and better prepare the community for the future? Does it reduce current and future risks associated with climate change? | [7 empty] | 2 | Low Effectiveness/Efficiency/Feasibility
Is the resilience action commensurate with the exposure and need? Can the "resilience strategy/action" be implemented in a timely manner and provide necessary reduction in vulnerability and risk that is comparable to the investment in the option over the lifespan of the project? | [7 empty] | 3 | Medium Effectiveness/Efficiency/Feasibility
Efficiency: The extent to which the resilience action makes efficient use of resources (funding, expertise, and staff time). | [7 empty] | 4 | High Effectiveness/Efficiency/Feasibility
What are the direct and indirect costs of the resilience action? Consider the life cycle costs (including initial upfront and long-term maintenance and operational costs) as well as indirect investments from staffing and other resource inputs necessary to complete the strategy/action. | [7 empty] | 5 | Very High Effectiveness/Efficiency/Feasibility
Are there any additional external costs? Consider environmental costs to species and habitats; negative community, social, or health impacts; and adverse economic benefits of the strategy/action.
Are there any additional benefits? Consider environmental benefits; community, social, recreational, or health benefits; and economic benefits of the action.
Is the resilience action flexible and robust? Consider whether the action can be modified over time as conditions change and how robust the action is to a variety of scenarios of change.
Feasibility: The extent to which the resilience action can successfully be implemented.
Is the resilience action institutionally feasible? Consider how institutional requirements and/or barriers affect the ease of implementation; the need to cross jurisdictional boundaries; or the necessity of multi-jurisdictional collaboration to make the strategy/action successful.
Is the resilience action technically feasible? Is the resilience action based on best practices and vetted approaches, can it be conducted with existing know how and technologies, and are there qualified professionals to support implementation?
Is the resilience action equitable? Consider if the resilience action promotes principles of justice, equity, diversity, and inclusion.
Is the resilience action politically feasible? Consider if the resilience action is broadly supported by the community, offers additional community benefits, and is well understood by the public.
Resilience Strategy/Action | Relevant Shock or Stressor | Timeframe for Implementation (when the action needs to be in place to be effective - not including lead time) | Total Cost (full cost of the action to implement) | Lead | Effectiveness (A score from 1-5 defining how "effective" the action may be) | Notes/Rationale | Efficiency (A score from 1-5 defining how "efficient" the action may be) | Notes/Rationale | Feasibility (A score from 1-5 defining how "feasible" the action may be) | Notes/Rationale | Total Score
Strategy 1:
Action 1
Action 2
Action 3
Strategy 2:
Action 1
Action 2
Action 3
Strategy 3:
Action 1
Action 2
Action 3
Strategy 4:
Action 1
Action 2
Action 3
Strategy 5:
Action 1
Action 2
Action 3

## S4A2 Final Actions
Community Readiness and Resilience Planning Toolkit Workbook: Step 4 Activity 2 Final Resilience Strategies and Actions
This tab will help your team finalize resilience strategies and actions as evaluated in Step 4, Activity 3. Use the additional columns to build out implementation details for your actions, including your draft indicators for success. See the Community Readiness and Resilience Toolkit for additional details (https://www.coresiliency.com/resilience-step-1).
Final Resilience Strategies and Actions | Resilience Value | Details | Initial Cost Estimates | Time for Implementation | Implementation Lead | Potential Partners | Indicators of Success | Opportunities for Mainstreaming
Strategy 1:
Action 1
Action 2
Action 3
Strategy 2:
Action 1
Action 2
Action 3
Strategy 3:
Action 1
Action 2
Action 3
Strategy 4:
Action 1
Action 2
Action 3
Strategy 5:
Action 1
Action 2
Action 3

## S5A3 Implementation Team
Community Readiness and Resilience Planning Toolkit Workbook: Step 5 Activity 3 Implementation Team Worksheet
Implementation of community resilience strategies requires support from a team. It also requires leadership and community buy-in. When thinking about the composition of your Community Resilience Implementation Team, consider involving the same representative groups formed during the previous phases including the core planning team, advisory committee, and various community stakeholders. However, it may be essential to expand this group to include additional community groups, businesses, departments, non-profit organizations, non-governmental organizations, and more.
Implementation Team
Last Name | First Name | Organization | Sector | Position/Department | Notes | Email | Phone
300 Tamalpais Drive, Corte Madera, CA

## S5A4 Action Implementation
Community Readiness and Resilience Planning Toolkit Workbook: Step 5 Activity 4 Action Implementation
This tab will help your team start to track the implementation of your resilience strategies/actions.
Resilience Actions | Approval | Current Status | To Be Updated
Strategy 1:
Action 1
Action 2
Action 3
Strategy 2:
Action 1
Action 2
Action 3
Strategy 3:
Action 1
Action 2
Action 3
Strategy 4:
Action 1
Action 2
Action 3
Strategy 5:
Action 1
Action 2
Action 3